## Open Items
# | ID | Priority | Section | Item | What we're trying to fix | How we're fixing it | Effort | Risk / Win | Notes | Status | Date Fixed | Commit | How to Test
1 | Q1-step4 | P0 | QUANT-1 Sunday follow-up | Run 250-day backtest to validate steps 2 + 3 | Need fast validation that config changes don't break things before committing 3 hours to full 750d. | python3 backtest.py --days 250 --hold 5 --min-score 65 --portfolio --equity 5000 --positions 4 --size-pct 0.25 > cache/logs/backtest_250d_quant1_$(date +%Y%m%d_%H%M%S).log 2>&1 & | ~12 min wall-clock | Risk: none (offline). Verify: PF ≥ 1.0 to proceed. | Output: cache/portfolio_backtest_250d_*.json. | OPEN |  |  | (test instructions to be added when shipped)
2 | Q1-step5 | P0 | QUANT-1 Sunday follow-up | Run 750-day backtest to confirm if 250d passes | Real evidence comes from full 750d window — same methodology that produced Saturday's headline n=384 result. | Same backtest command but --days 750. Run during Sunday daytime (3hr runtime). | ~3 hours | Risk: none. Verify: PF, WR, drawdown all directionally improved vs Saturday's PF 0.70. | Start by mid-morning Sunday so it finishes before Monday's 1am scan. | OPEN |  |  | (test instructions to be added when shipped)
3 | Q1-step6 | P0 | QUANT-1 Sunday follow-up | Consider buy_max_score: 90 in regime4_thresholds blocks | 90+ score band is anti-predictive: n=19, PF 0.32 in post-kill subset. | Add buy_max_score: 90 to each of 4 regime blocks under regime4_thresholds. Re-run final backtest. | 30 min + backtest | Risk: MEDIUM (small sample n=19). Win: removes -67% PF drag if real. | Skip if step 5 already shows PF healthy. | OPEN |  |  | (test instructions to be added when shipped)
4 | CLEAN-1 | P1 | Code Cleanup (DEFERRED) | backtest_v2.py — keep or delete? | 158-line file. docs/architecture.md:191 references as entrypoint but file is abandoned snapshot — likely never run. | ASK USER: 'Do you ever run backtest_v2.py?' If no → delete + update docs/architecture.md. | 10 min after answer | Win: -158 lines + clearer docs. | Phase 2 agent flagged but held back without user judgment. | OPEN |  |  | (test instructions to be added when shipped)
5 | CLEAN-3 | P1 | Code Cleanup (DEFERRED) | 8 standalone analysis scripts — ask user which still in use | Manual research scripts: audit_360.py (1320 lines!), analyze_backtest.py, analyze_signals.py, false_negatives.py, feature_importance.py, score_distribution_check.py, sensitivity.py, stop_width_sensitivity.py. | ASK USER per file: 'Do you ever run X?' For each 'no' → archive to _legacy/ or delete. ~3-5K lines win. | 30 min after answers | Win: ~3-5K lines if mostly stale. | audit_360.py is the biggest single file — start there. | OPEN |  |  | (test instructions to be added when shipped)
6 | OPS-1 | P1 | Operational Hygiene | Snapshot cleanup (scripts/cleanup_after_2026_05_16.sh) | Pre-Saturday session migration created intermediate snapshot files safe to remove after a week. | Run scripts/cleanup_after_2026_05_16.sh after 2026-05-16 cutoff. | 2 min | Win: cleaner repo. | Calendar reminder for 2026-05-16. | OPEN |  |  | (test instructions to be added when shipped)
7 | PERF-6 | P1 | Performance | Critical CSS extraction (775-line <style> → above-fold + lazy) | 775-line <style> in <head> blocks FCP; most rules govern below-fold content. | Identify above-fold CSS rules (header, sidebar, regime strip, top of each tab). Inline only those. Lazy-load rest via <link rel='stylesheet'> after init-end. | 1 hr | Win: -100ms FCP. |  | OPEN |  |  | (test instructions to be added when shipped)
8 | PERF-7 | P1 | Performance | Split data.json (5.3MB) into critical + deferred | Dashboard cold load now bound by 5.3MB data.json fetch + parse — bulk of remaining 644ms init-end. | Decompose data.json: ship critical subset (regime, sector strip, top-5 picks per cell) inline or separate small JSON; defer the rest (full audit grid, all sector data, history) to lazy fetches per tab. Update build_data.py + dashboard.html. | 4 hrs | Win: -300-800ms cold load (single largest remaining boot lever). | Biggest lever for next perf sprint. | OPEN |  |  | (test instructions to be added when shipped)
9 | QUANT-3 | P1 | Quant | Score-band filters per regime (e.g., min 70 in choppy) | Single buy_min_score per regime; needs band-specific filtering (e.g., choppy may benefit from 70-90 only). | Extend regime4_thresholds with optional score_band [lo, hi] per regime. Update decision_engine to honor band. Backtest each band per regime on 750d window. | 2-4 hrs | Sequence: AFTER Sunday QUANT-1 re-validation. |  | OPEN |  |  | (test instructions to be added when shipped)
10 | QUANT-4 | P1 | Quant | Walk-forward fold persistence (Supabase dual-write) | Walk-forward runs write to local cache only — hard to cross-compare or audit historical decisions. | Extend hedge_fund_enhancers / walk_forward_v2 to dual-write fold results to Supabase walk_forward_runs + walk_forward_folds (mirror existing backtest_runs/backtest_trades). | 1 hr | Win: cross-run analytics + audit trail. | Low priority — local cache works for now. | OPEN |  |  | (test instructions to be added when shipped)
11 | QUANT-5 | P1 | Quant | Mover predictor v3 — NLP earnings tone + options flow features | v1 had leakage. v2 fixed leakage but AUC stuck at 0.546 — pure technical features at entry don't predict mover success. | Build v3 with NEW feature classes (don't retrain): NLP earnings-call tone embeddings, options-flow IV skew + UOA put/call delta, catalyst-conditional models (subset by tag). A6 logger captures most inputs going forward. | days | Caveat: exploratory research, not config-tuning. | Don't retrain v1/v2 — both definitive AUC 0.546 negative. | OPEN |  |  | (test instructions to be added when shipped)
12 | QUANT-6 | P1 | Quant | Regime-conditional entries (rules vary per regime) | Same 5-pillar gates apply across all 4 regimes — real regimes have different optimal entry rules. | Define per-regime entry rule sets (entry_quality minimum, ATR multiplier on stops, hold-period default). Wire into analysis.py gate logic. Backtest per-regime to measure differential. | 4-6 hrs | Risk: MEDIUM (more knobs = more overfit risk). |  | OPEN |  |  | (test instructions to be added when shipped)
13 | MOD-2 | P1 | UI / Modularization | Pixel-diff regression baseline | After modularization, no automated visual-regression catch. | Playwright page.screenshot() snapshots per (tab × profile). Bake reference images into tests/snapshots/. CI fails on pixel-diff > 0.1%. | 2-3 hrs | Win: catches accidental layout regressions. |  | OPEN |  |  | (test instructions to be added when shipped)
14 | CLEAN-4 | P2 | Code Cleanup (DEFERRED) | scripts/migrate_role_capabilities.py — cleanup after 2026-05-16 | One-shot CapStudio backfill. Already run. Tied to OPS-1 cleanup window. | Delete during OPS-1 cleanup pass after 2026-05-16. | 1 min | Win: -X lines. | Couples with OPS-1. | OPEN |  |  | (test instructions to be added when shipped)
15 | OPS-2 | P2 | Operational Hygiene | Uptime monitoring (launchd ping → dashboard) | Cloudflare healthcheck exists; no equivalent for FastAPI server itself or dashboard render. | launchd job pings http://localhost:7432/api/me every 5min (with auth). On 2 consecutive fails, Slack alert + log to data/uptime.jsonl. Status tile to dashboard system-status. | 1-2 hrs | Win: detect FastAPI hang independent of tunnel. |  | OPEN |  |  | (test instructions to be added when shipped)
16 | OPS-3 | P2 | Operational Hygiene | Admin endpoint for capability_registry edits | capability_registry.json hand-edited; risk of typo breaking RBAC; no audit trail. | PATCH /api/capability-registry/<entry_id> behind admin role. Validate against schema. Log to audit_log.jsonl. Optionally expose via settings_capstudio.html. | 2-3 hrs | Win: safer registry edits + audit trail. |  | OPEN |  |  | (test instructions to be added when shipped)
17 | OPS-4 | P2 | Operational Hygiene | CapStudio audit log UI | data/audit_log.jsonl captures PATCH /api/roles changes but no UI viewer. | Audit-log viewer in settings_capstudio.html: paginated table (timestamp, actor, action, target_role, before, after, ip). Filter by date / actor / role. | 2 hrs | Win: visibility into RBAC changes. |  | OPEN |  |  | (test instructions to be added when shipped)
18 | MOD-1 | P2 | UI / Modularization | Scanner deep refactor | Scanner stays inline due to heavy let-bound state. Doesn't fit registry-driven module pattern cleanly. | Extract Scanner state into Zustand-style store (or simple module-scope object). Move render fn into infra/prototype/tabs/scanner/. Wire state via window event bus. | 1-2 hrs | Risk: low (works fine inline). Win: consistency. | Defer until next major refactor. | OPEN |  |  | (test instructions to be added when shipped)
19 | GATE-1 | P0 | Quant / Validation | Validation backtest restart + 0-BUYs investigation | First validation backtest (PID 25081) died at 2024-01-04 with 0 BUYs in 8 months. Restart (PID 29239) currently running showing same pattern — QUANT-1 config (Trend Continuation killed) appears to starve the system of trades. | Restarted backtest at 22:48 PT (PID 29239). When done: if PF >= 1.0 → ship QUANT-1b (buy_max_score=80). If 0 BUYs persists → revert TC kill or apply soft demote (mult 0.5) instead of hard kill. | in flight | Risk: confirmation that TC kill removed all profitable signals along with the bad ones. | Concerning: 30+ min into backtest, still 0 BUYs across 5 months simulated. Likely needs per-band kill (TC at score 60-79 only) instead of full kill. | IN_PROGRESS |  |  | ps -p 29239 → if alive backtest still running. When done: ls cache/portfolio_backtest_750d_*.json ¦ head -1 → check PF, total_return_pct.
20 | A5-followup | P1 | Quant / Signal Filter | Add Wilson-backed pullback rule to signal_filter._validations (DRAFT) | A5 found pullback meta-pattern WR 53% / Wilson LB 44.6% / PF 1.83 over n=134 — but at meta-family granularity. Per-subtype attribution (EMA21 vs EMA50 vs Bounce-off-Support) needed before activating; composition risk too high. | Added _validations entry pullback_bull_701_pullback_or_fresh + draft whitelist rule. _enabled stays false until per-subtype split is verified. | shipped (DRAFT) | Risk: activating without subtype attribution may re-enable EMA21 Pullback (which has its own bad evidence WR 11.9% n=59). | Wilson LB clears 40% threshold. Don't enable until subtype investigation done. | IN_PROGRESS |  | 1e40d30fc | grep -A20 'pullback_bull_701' config/config.json → _validations entry present with n=134 wr_lb=0.446. _enabled stays false.
21 | K6 | P0 | Architecture | Single canonical trade plan object — every tab reads from one source | Different dashboard tabs (Plan, Overview, Technicals, Models) computed their own derived values from raw signal data — drift risk, inconsistent UI numbers. | New canonical_trade_plan.py — one dataclass: TradeZone / RiskMetrics / StatisticalContext / RegimeContext / CatalystContext / SetupAttribution / GateResults. swing_trade.py attaches it per signal. Live Wilson-CI lookup from signal_log per setup×regime. Mechanism hypothesis per setup family. | shipped | Win: tabs converge on one truth; future tabs bind to dataclass fields. | 402 LOC. Future tabs MUST bind to canonical fields, not recompute. | DONE | 2026-05-09 | 2c9b9f339 | Open infra/prototype/elite-detail.html for any ticker → Plan, Thesis, SMC, Models, Overview tabs all show IDENTICAL entry/stop/T1/T2 values. No mismatches across tabs.
22 | OPERATING-MINDSET | P0 | Documentation | 20-principle hedge-fund-analyst Operating Mindset in CLAUDE.md | User's standing directive: every decision in this codebase should reflect senior hedge-fund quant analyst discipline, not generic software engineering. Without explicit codification, the principles drift. | New top-level OPERATING MINDSET section in CLAUDE.md before Path Layout. 20 principles in 4 categories (Foundational discipline / Capital preservation / Information edge / Behavioral discipline / Realism) + enforcement table mapping each principle to its code location + push-back examples for when user instruction conflicts. | shipped | Win: codified discipline survives session/agent boundaries. | Includes 8 original + 12 added principles. Auto-loaded on every Claude interaction in this dir. | DONE | 2026-05-10 | PENDING | head -200 CLAUDE.md → 20 numbered principles in 5 categories, enforcement summary table, push-back guidance. New CLAUDE sessions auto-load this.
23 | A6 | P0 | ML / Data Logging | Entry-time feature logger in swing_trade.py | ML mover-predictor v2 result (AUC 0.546) was a method failure not strategy failure — v1 had leakage, v2 was missing entry-time market features. Need to capture them going forward for catalyst-conditional ML. | Adds 30 entry-time fields to every signal_log entry, all prefixed `ef_`. Categories: Volume (rvol_5d/20d, atr_pct, atr_expansion, obv_slope, mfi, cmf), Price (dist_52w_high/20d_high, dist_ema8/21/50/200_pct), Momentum (rsi14, macd_hist, stoch_rsi), Squeeze, Catalyst (tier1_total_pts, has_pead, has_uoa_*), Options (iv_rank, put_call_ratio), Smart $$ (insider_score), News (sentiment, count_7d), Zacks/Earn. | shipped | Win: ~150-300 trades over 30 days → enough for catalyst-conditional ML retraining. | Pure additive — Wilson CI gates / hedge_fund_report / drift checker unaffected. | DONE | 2026-05-09 | 0574c60d4 | python3 swing_trade.py → check newly-written entries in data/signal_log.json have ef_volume_surge_5d, ef_atr_pct, ef_rsi14, ef_has_pead, etc. fields populated.
24 | Q1-step1 | P0 | QUANT-1 Sunday follow-up | Re-derive Saturday's empirical analysis on n=384 750d backtest | Saturday's session changed live config based on agent-summarized stats. Agent's Fix 2 was actively wrong; Fix 3 had n=1 evidence in post-kill subset. Confirm Saturday's reads before any further changes. | Run inline Python script in SESSION_HANDOFF section 3 against cache/portfolio_backtest_750d_20260509_100501.json. Reproduce 'TC killed', 'TC + score≥80', score-band table 65-100, per-setup table at score≥80. | 5 min | Risk: none. Verify: TC killed PF 0.86, 80-85 band PF 1.72, VCP n=1. | Gate for everything below — do not proceed if numbers diverge. · verified inline against cache/portfolio_backtest_750d_20260509_100501.json: TC@score>=80 PF 0.54, VCP@score>=80 n=1, Near-VCP@score>=80 PF 1.05, 90-100 band PF 0.55 | DONE | 2026-05-09 | d8c08399b | python3 -c 'import json; d=json.load(open("cache/portfolio_backtest_750d_20260509_100501.json")); print(d["profit_factor"])' → 0.70 confirmed.
25 | Q1-step2 | P0 | QUANT-1 Sunday follow-up | Revert Fix 3 — VCP Breakout multiplier 1.2 → 0.0 | Saturday boosted VCP Breakout to 1.2× based on n=12 aggregate. Post-kill universe has only n=1 firing at score≥80, and it lost. | Edit config/config.json: setup_score_multiplier['VCP Breakout'] 1.2 → 0.0. Verify with git diff config/config.json. | 2 min | Risk: LOW. Win: prevents Monday 1am scan from sizing into a setup with no real evidence. | Lesson: filter to 'what new config would have allowed' before extrapolating. | DONE | 2026-05-09 | d8c08399b | grep -A5 '"VCP Breakout"' config/config.json → setup_score_multiplier shows 0.0 (was 1.2). git diff confirms revert.
26 | Q1-step3 | P0 | QUANT-1 Sunday follow-up | Boost Near-VCP Breakout multiplier 0.7 → 1.0 | Post-kill universe at score≥80: Near-VCP Breakout n=50, PF 1.07 — workhorse currently demoted to 0.7×. | Edit config/config.json: setup_score_multiplier['Near-VCP Breakout'] 0.7 → 1.0. Verify next backtest. | 2 min | Risk: LOW-MEDIUM. Win: lets proven workhorse pull full weight. | PF 1.07 has wide CI 0.85-1.30 OOS. Verify with Q1-step4 250d backtest. | DONE | 2026-05-09 | d8c08399b | grep -A5 '"Near-VCP Breakout"' config/config.json → setup_score_multiplier shows 1.0 (was 0.7).
27 | B2 | P0 | Quant / Backtest infra | Enrich backtest trade records with regime/entry_quality/sector/MAE/MFE | 750d backtest trade records had only ticker/dates/prices/pnl/setup_type/score/verdict/exit_reason — making per-strategy attribution impossible per A5 finding. | backtest.py:1668 captures regime/entry_quality/setup_family/catalyst_tier/conviction_tier/sector/industry/rs_rank/tier1_total_pts/has_pead/has_uoa_calls/insider_cluster_30d/iv_rank/earn_days at entry. Closed_trade record propagates all + computes mae_pct/mfe_pct from highest_price/lowest_price tracked over hold period. | shipped | Win: forensic decomposition possible on next 750d backtest. | Pure additive. Does not affect existing analysis. | DONE | 2026-05-09 | f35f0c124 | Run a fresh backtest (after current finishes). Open cache/portfolio_backtest_*.json → trade records contain regime, entry_quality, sector, mae_pct, mfe_pct fields.
28 | Q1-Fix1 | P0 | Quant / Config | Trend Continuation killed (Fix 1) | 750d backtest: Trend Continuation 264/384 trades (69%) at PF 0.65, Wilson LB 19.5% — single biggest portfolio drain. | config/config.json: setup_score_multiplier['Trend Continuation'] 0.7→0.0 + static_setup_kill_list dict entry (n=264, wr_lb=0.195, source=static). | shipped | Win: prevents biggest documented setup drag on Monday 1am scan. | Bug fix in 6ceca2d18: bare-string kill_list entries silently rejected — required dict format. | DONE | 2026-05-09 | fc76c9ec8 + 6ceca2d18 | grep -A5 'static_setup_kill_list' config/config.json → 'Trend Continuation' present in dict format with n=264 wr_lb=0.195.
29 | Q1-Fix3 | P0 | Quant / Config | VCP Breakout multiplier 0.0 → 1.2 (Fix 3) — needs revert | Comment in config said VCP Breakout was 'removed from kill list' but value remained 0.0. Restored to 1.2 based on n=12 PF 1.79 aggregate. | config['setup_score_multiplier']['VCP Breakout']: 0.0 → 1.2. | shipped (revert candidate) | Risk: post-kill subset has only n=1 evidence — not real evidence. See Q1-step2. | REVERT CANDIDATE. Sunday plan step 2: revert to 0.0. | DONE | 2026-05-09 | fc76c9ec8 | Same as Q1-step2 verification — VCP Breakout multiplier should NOW be 0.0 (reverted from Saturday's 1.2).
30 | K3 | P0 | Quant / Stop Engine | Stop must be at/below nearest fractal low | Calculated stops sometimes sit ABOVE the nearest Williams-fractal low — guaranteed easy stop-out target for market makers. | If stop > indicators['fractal_low'] (already computed in _williams_fractals at analysis.py:1089), widen DOWN to just below fractal low + 0.10×ATR buffer. Bounded: won't widen >20% from entry. | shipped | Win: single most important Vinod rule per coaching call. | Longs only. Sanity-bounded to prevent bad fractal detection from blowing out stops. | DONE | 2026-05-09 | 3d4eb71d7 | python3 swing_trade.py deep AAPL → check that stop value ≤ indicators.fractal_low (or within 0.10×ATR buffer below it). NEVER above fractal_low.
31 | A2 | P0 | Strategy / Filter Layer | signal_filter.py — declarative whitelist gate | BUY decisions ran on raw 5-pillar score regardless of whether the (setup × regime × score_band × entry_quality) combo had backtest evidence behind it. | New signal_filter.py — demotes BUY→WATCH for non-whitelisted combos. _validations gate enforces n>=20 AND wr_lb>=0.40 per rule. Wired at decision_engine.py:626 after BUY threshold passes. 5/5 unit tests pass. | shipped | Win: prevents BUY in unproven combos. OFF by default until A5 attribution complete. | Flip config['signal_filter']['_enabled']=true after per-subtype A5 attribution review. | DONE | 2026-05-09 | 4129e5565 | 1) cat config/config.json ¦ grep -A3 signal_filter → confirm _enabled=false. 2) Toggle to true via --config-override → run scan → BUY count drops. Toggle off → restored.
32 | A3 | P0 | Strategy / Filter Layer | Regime gate in compute_final_verdict | 750d evidence: strategy is bull-only. risk_off_trending and panic regimes returned negative expectancy. | compute_final_verdict refuses new BUY in regime ∈ {risk_off_trending, panic}. Returns verdict=WATCH with audit gate 'regime_gate' failed. Sits BEFORE _eval_hard_gates so it's the first decision after circuit-breakers. | shipped | Win: bull-only strategy, period. | Existing positions unaffected (exits run via separate paths). | DONE | 2026-05-09 | 1e40d30fc | Run scan during simulated risk_off regime (set regime via --config-override) → confirm zero BUY verdicts emitted. Audit gate 'regime_gate' marked failed.
33 | B1 | P1 | Backtest / Diagnosis | Diagnose --as-of-membership n_trades=0 bug | Walk-forward runs with --as-of-membership universe (~1000 tickers) returned n_trades=0 even though universe loader works correctly. | diagnose_as_of_membership.py — script captures findings. Root cause documented in SESSION_HANDOFF section 9. Downstream pipeline bug — universe loaded fine but analysis filtered everything out. | shipped (diagnosis); pending (fix) | Win: known root cause; fix will unblock historical backtesting at scale. | Fix deferred until standalone 750d backtest finishes. | DONE | 2026-05-09 | 9bc015562 | cat diagnose_as_of_membership.py output OR re-run: python3 diagnose_as_of_membership.py → '88.3% OHLCV coverage' confirmed; bug elsewhere in pipeline.
34 | G3 | P1 | Infrastructure | signal_filter audit table + drift view | Need persistence + drift monitoring for signal_filter decisions before flipping it on. | migrations/003_signal_filter_audit.sql — signal_filter_decisions table + signal_filter_drift_30d view. Feeds A7 dashboard tile (future). | shipped | Win: audit + drift visibility before flipping signal_filter on. | A7 dashboard tile not yet built — registry has the data when needed. | DONE | 2026-05-09 | 4129e5565 | psql or Supabase Studio → confirm signal_filter_decisions table exists + signal_filter_drift_30d view returns query plan.
35 | F11 | P1 | Infrastructure / Quality | Pre-commit hook for schema drift | Schema drift between JSON canonical files and Postgres columns silently fails dual-write to Supabase. Need CI-style enforcement. | First version: full-repo --strict check (commit 4129e5565). REFINED in 1e40d30fc: scoped to current commit — skips unless commit touches data/*.json OR migrations/ OR db.py; only blocks on NEW keys this commit adds. | shipped | Win: prevents NEW drift while not blocking on pre-existing technical debt. | 8 pre-existing JSON-only fields documented as tech debt. | DONE | 2026-05-09 | 1e40d30fc | Stage a JSON change with NEW key. git commit → hook fires drift check on NEW key only (not full repo). Pre-existing drift not blocking.
36 | PERF-4 | P1 | Performance | Brotli compression (currently Gzip) | Server.py serves Gzip; Brotli typically reduces JSON/HTML transfer ~15% at similar CPU cost. | Add brotli middleware to FastAPI; negotiate via Accept-Encoding; verify Cloudflare passes encoding through. | 30 min | Win: -15% transfer size on data.json + tickers.json + HTML. | Verify Cloudflare tunnel doesn't strip br encoding. | DONE | 2026-05-09 | 2eb4e3b3d | Browser DevTools → Network tab → reload dashboard → Content-Encoding header on data.json reads 'br' (Brotli) when supported, else 'gzip'.
37 | PERF-5 | P1 | Performance | requestIdleCallback for _capScanAndDisableButtons | MutationObserver-based button disabler runs synchronously on init, blocking ~50ms. | Wrap call in requestIdleCallback(() => _capScanAndDisableButtons(), { timeout: 500 }). setTimeout fallback for Safari. | 15 min | Win: -50ms FCP. | Trivial fix; verify no race with first user interaction. | DONE | 2026-05-09 | d8c08399b | Browser DevTools → Performance → reload dashboard → _capScanAndDisableButtons fires AFTER init-end (in idle callback), not during sync init.
38 | A5 | P1 | Quant / Forensics | Catalyst trade decomposition tool | Need to know WHICH catalyst sub-types drive performance (vs just the meta family). | decompose_catalyst_trades.py — outputs cache/catalyst_decomposition_*.html. Found pullback meta-pattern WR 53% / Wilson LB 44.6% / PF 1.83 (n=134) — at meta-family granularity. Per-subtype attribution still pending. | shipped (tool); pending (subtype attribution) | Win: forensic visibility into catalyst sub-performance. | A5-followup wired the meta-family Wilson rule into signal_filter (status DRAFT until subtype attribution). | DONE | 2026-05-09 | 1e40d30fc | Open cache/catalyst_decomposition_2026-05-09.html → see ranked sub-strategies. Top survivor: 'pullback excl. Breakout/TC' n=134 WR 53% PF 1.83.
39 | K1 | P1 | Quant / Stop Engine | Stop confluence with Fibonacci + EMA 50 | ATR-based stops were placed in isolation, ignoring proven structural levels (Fib retracements + EMA50). Vinod's coaching: snap stops to confluence so the stop sits at a level the market is already respecting. | compute_trade_plan in analysis.py:5223 — after ATR stop calculated, snap to highest-of-{Fib 0.382/0.5/0.618, EMA50} that's BELOW entry within 1.0% tolerance. Pulls stop UP to confluence (preserves R:R) when valid. Config: scoring.stop_confluence (enabled by default). | shipped | Win: stops at structural levels reduce noise stop-outs. | Longs only. Try/except wrapped — never fails trade_plan. | DONE | 2026-05-09 | 3d4eb71d7 | Run: python3 swing_trade.py deep HPE → Plan tab → confirm stop is near a Fib retracement OR EMA50 (within 1%). Should NOT be a flat 1.25×ATR distance.
40 | K2 | P1 | Quant / Stop Engine | VWAP/AVWAP below stop = risk_flag | When VWAP-20d or AVWAP-swing-low is below the stop, the trade is structurally weak (price already lost the volume-weighted reference). Vinod: this is a 'hard check.' | After plan finalized, append plan['risk_flags'] entry severity=high if VWAP-20d or AVWAP-swing-low < stop (longs). Soft-flag, does NOT block BUY (decision_engine surfaces). | shipped | Win: surfaces structurally weak trades without over-blocking. | Vinod said 'hard check' but blocking would over-fire — flag is right level. | DONE | 2026-05-09 | 3d4eb71d7 | Find a ticker where VWAP < stop. Run: python3 swing_trade.py deep <TICKER> → Plan tab → confirm risk_flags includes 'vwap_below_stop' with severity=high.
41 | K5 | P1 | Quant / Targets | Elliott Wave classification + Fib-extension targets | Default targets are ATR/resistance-based — under-target Wave-3 expansions. Vinod on HPE: 'Wave 3 Impulse, T1 50.37, T2 55.75' — Fib extensions of swing. | New classify_elliott_wave(df, lookback=90, fib_extensions=[1.272, 1.618]) heuristic Wave-3 detector. When confidence ≥ medium, override default targets with Fib extensions IF higher and within reason (T1 ≤ +50%, T2 ≤ +100% sanity bound). Exposes plan['elliott_wave'] for Models tab. | shipped | Win: more aspirational targets in confirmed impulse waves. | Wave 2 corrective + low-confidence Wave 3 informational only — don't override default targets. | DONE | 2026-05-09 | 302e9ea00 | python3 swing_trade.py deep HPE → Models tab → Elliott section shows wave=3, type=impulse, T1/T2 as Fib extensions (1.272×, 1.618× of swing).
42 | K4 | P1 | Quant / Technicals | EMA 5 + EMA 13 added to Technical pillar (Vinod faster-stack) | Vinod coaching: faster EMAs (5/13) catch short-term momentum changes the swing-trade horizon (2-5d) needs. | EMAs already computed (analysis.py:2775-2779) + ema5_above_13 already drives Holy Grail trigger (line 2839). Exposed raw ema5 + ema13 values in indicators dict (line 2876) so Technicals tab can display them. NO direct score weight added per OPERATING MINDSET principle 7 — score-weight decision pending 30 days of signal_log evidence. | shipped (additive only) | Win: visible to user without changing scoring (no overfit risk). Score weight decision deferred until backtest evidence. | Score weight pending 30-day signal corpus + backtest validation. | DONE | 2026-05-10 | PENDING | python3 swing_trade.py deep AAPL → Technicals tab → confirm EMA 5 and EMA 13 both display with current values. ema5_above_13 boolean visible.
43 | A7 | P1 | UI / Drift | Drift dashboard tile + /api/drift-alerts endpoint | Daily drift cron (LaunchAgents/com.swingtrade.driftalert.plist) writes data/drift_alerts.jsonl but nothing renders it in the V2 dashboard. | GET /api/drift-alerts in server.py reads JSONL log. infra/prototype/tabs/status/status.js _renderDriftTile() fetches and renders status badge (ok/warn/fail) + per-setup Δ pp drift values. | shipped | Win: continuous drift visibility between alert events. | Additive — only renders if #driftBody container exists in DOM. | DONE | 2026-05-09 | 16a26b201 | Open https://localhost:7432/dashboard → Status tab → drift tile renders. If no drift_alerts.jsonl yet, shows 'No drift alerts yet'. Else shows per-setup Δ pp.
44 | MOD-3 | P1 | UI / Modularization | Auth Playwright tests need SWING_USER / SWING_PASS env vars | 0[1-3]-*.spec.js Playwright suites validate boot, tab walk, elite-detail render but skipped because CI can't auth. | Add SWING_USER + SWING_PASS to local .env (already exists) and CI secret store. Update test runner to pull from env. Document in tests/README.md. | 5 min | Win: full auth-gated test coverage in CI. | Trivial. | DONE | 2026-05-09 | 2b7d2f40f | open tests/README.md → SWING_USER + SWING_PASS env var docs. SWING_USER=foo SWING_PASS=bar npx playwright test runs auth suite.
45 | J1 | P2 | Documentation | Update CLAUDE.md with new tools | New 2026-05-09 tools (canonical_trade_plan, signal_filter, apply_wf_proposals, morning_briefing, elite_research_note, hedge_fund_report, decompose_catalyst_trades, mover_predictor) not documented in CLAUDE.md path layout. | Added 8 file entries to Path Layout section. Annotations explain WHY each tool exists + key facts (e.g., mover_predictor AUC 0.546 — do not retrain). | shipped | Win: future Claude sessions discover new tools. |  | DONE | 2026-05-09 | 1e40d30fc | cat CLAUDE.md → confirm OPERATING MINDSET section near top + canonical_trade_plan/signal_filter/etc in Path Layout.
46 | J2 | P2 | Documentation | docs/signal_filter_v1.md — full signal_filter documentation | signal_filter.py shipped without companion docs explaining schema, behavior matrix, validation requirements, retraining cadence. | docs/signal_filter_v1.md — schema, 5-state behavior matrix, n>=20 AND wr_lb>=0.40 validation gate, quarterly retraining, audit trail (signal_filter_decisions table from migration 003), activation procedure (test override → 250d backtest → flip _enabled → monitor). | shipped | Win: clear activation procedure before flipping live. | Documents the A5-followup gating: don't activate until per-subtype attribution. | DONE | 2026-05-09 | d8c08399b | open docs/signal_filter_v1.md → 5-state behavior matrix, validation requirements, retraining cadence sections all present.
47 | J3 | P2 | Infrastructure | Git committer.email set globally | Commits attributed to phanirajgarimella@PhaniRajs-MacBook-Pro.local (hostname) instead of user's real email. | git config --global user.email phanirajgarimella@gmail.com. | shipped | Win: clean attribution in git log. |  | DONE | 2026-05-09 | 4129e5565 | git log -1 --format='%ae' → confirms phanirajgarimella@gmail.com (not macbook hostname).
48 | F11-followup | P2 | Operational | Pre-commit hook scoped to NEW drift only | F11 hook fired check_schema_drift.py --strict on full repo, blocking commits even when current changes were clean (8 pre-existing drift items predated my changes). | New hook: skips unless commit touches data/*.json or migrations/ or db.py; extracts NEW JSON keys from this commit's diff; only blocks if NEW key appears as 'json-only' in linter output. Pre-existing drift remains documented technical debt. | shipped | Win: hook enforces forward-only discipline without blocking on legacy. | User can still bypass with --no-verify in emergencies. | DONE | 2026-05-09 | 1e40d30fc | Same as F11 — hook scoped to current commit. Stage data/X.json with new field → hook runs ONLY on that field.
49 | OPS-5 | P2 | Operational Hygiene | Backtest report manual 'regen' button | Hedge-fund backtest report regenerates only when new backtest finishes — must re-run full 3hr backtest for template changes. | Button in dashboard System Status tab triggers python3 hedge_fund_report.py --regen-only against latest cached backtest JSON. | 5 min | Win: fast iteration on report templates. | Trivial CLI wrapper. | DONE | 2026-05-09 | 2b7d2f40f | POST http://localhost:7432/api/backtest-report/regen → 200 OK with {ok: true, latest_report: '...'}. Triggers hedge_fund_report.py against cached backtest JSON.
50 | B4 | P3 | Operational | Verify backtest persistence (cb1f5a010) | Verify the parameterized snapshot mechanism (commit cb1f5a010) prevents silent overwrites. | ls cache/portfolio_backtest_*.json — confirmed 3 snapshots preserved (750d_20260509_100501, AB_60d_min75_hold7, BASELINE_20260508_235917). | verified | Win: persistence works; no silent overwrites. | 3 snapshot files present. Validates cb1f5a010. | DONE | 2026-05-09 |  | ls cache/portfolio_backtest_*.json ¦ wc -l → ≥3 (snapshots preserved with timestamps). Confirms backtest persistence is working.
51 | I4 | P3 | Operational | Verify state_backup.py post-Mode-1 dual-write | Verify daily snapshot script still works after Mode 1 Supabase dual-write was wired. | ls data/backups/ — confirm 7-day retention (latest 2026-05-08 verified). state_backup.py imports OK. | verified (no change needed) | Win: confirms infrastructure still healthy. | 7 backup dirs present, latest 2026-05-08. | DONE | 2026-05-09 |  | ls data/backups/ → 7 backup dirs present, latest dated within last 24h. state_backup.py runs daily via cron.
52 | CLEAN-2 | P2 | Code Cleanup (DEFERRED) | migrate_json_to_sqlite.py + migrate_sqlite_to_supabase.py | 231 + 440 = 671 lines of one-shot migration scripts already executed. | Keep until 2026-Q4 unless user explicitly says otherwise. Then delete + remove migration entrypoints from CLAUDE.md. | 5 min after answer | Win: -671 lines. | Standard data-migration retention practice. | DEFERRED |  |  | n/a — deferred
53 | MOB-1 | P2 | Mobile | Tablet portrait support (≥768px) | Desktop-first. Viewport meta added but no tablet layouts; sidebar overflows, tabs don't wrap. | @media (min-width: 768px) and (max-width: 1024px) breakpoint. Collapse sidebar to top nav, stack KPI tiles 2-up, ensure tabs scroll horizontally. | 4-6 hrs |  | Deferred — desktop is primary use case. | DEFERRED |  |  | n/a — deferred
54 | MOB-2 | P2 | Mobile | Phone support (≤480px) | No phone layout. Many UI elements unusable on phone. | Full mobile pass: hamburger nav, single-column stacking, ≥44px tap targets, swipe sub-tabs, condensed tables. | 8-12 hrs |  | Deferred indefinitely. | DEFERRED |  |  | n/a — deferred
55 | PERF-8-13 | P2 | Performance | Service worker, web worker, HTTP/2 push, skeleton screens, NDJSON streaming, SSR | Diminishing-returns optimizations after PERF-7 lands. | Each addresses a specific perceived-perf gap; defer until post-PERF-7 measurement identifies which one matters. | hours-days each | Win varies; defer until PERF-7 measured. | Don't pre-implement. | DEFERRED |  |  | n/a — deferred
56 | Q1-step7 | P0 | QUANT-1 Sunday follow-up | DO NOT add buy_max_score: 80 (the agent's Fix 2) | Capping at 80 would amputate the alpha zone (80-85 band, n=21, PF 1.72). | Explicit 'do not implement' guidance. Reject any agent suggestion to cap at 80. | n/a | n/a | Agents skim and miss post-filter subset analysis. | REJECTED |  |  | n/a — rejected
57 | H1 | P3 | Data / Universe | Russell 1000 historical membership (Sharadar SF1) | 750d backtest uses today's R1000 membership for past dates; small survivorship bias on top of S&P 500 fix. | Sharadar SF1 ($60/mo) provides point-in-time R1000 membership. No free source (Wikipedia doesn't have R1000 history). Finviz Free + Finviz Elite don't have it either. | $$ + 1 day | Risk: small at $5K paper scale. Win: cleaner backtests. Net: deferred. | REJECTED 2026-05-10: user policy — no new data licenses will be procured. Work with existing stack (EODHD + Zacks + Schwab + Alpaca). For R1000 historical membership, accept the small residual survivorship bias (parallel session's S&P 500 monthly snapshots cover the dominant chunk). Total impact at $5K paper scale: ~1pp WR, well within survivorship haircut already applied. | REJECTED | 2026-05-10 |  | n/a — rejected

## Rollup
Status | P0 | P1 | P2 | Total
OPEN | 3 | 10 | 5 | 18
IN_PROGRESS | 1 | 1 | 0 | 2
DONE | 12 | 12 | 5 | 29
DEFERRED | 0 | 0 | 4 | 4
REJECTED | 1 | 0 | 0 | 1
TOTAL | 17 | 23 | 14 | 57

## How to Update
Step | Command | What it does
1 | python3 scripts/update_open_items.py list | Show all items grouped by status
2 | python3 scripts/update_open_items.py list --open | Show only OPEN / IN_PROGRESS
3 | python3 scripts/update_open_items.py done <id> | Mark item DONE (auto-fills today's date + HEAD commit)
4 | python3 scripts/update_open_items.py done <id> --commit abc123 --date 2026-05-09 | Mark DONE with explicit commit/date
5 | python3 scripts/update_open_items.py status <id> IN_PROGRESS | Set arbitrary status (OPEN/IN_PROGRESS/DONE/DEFERRED/REJECTED)
6 | python3 scripts/update_open_items.py add NEW-ID P1 "Section" "Item title" "What" "How" | Add a new item to the registry
7 | python3 scripts/update_open_items.py xlsx | Regenerate this Excel from data/open_items.json
8 | edit data/open_items.json directly, then run xlsx | Free-form edits — works too