## Open Items
# | ID | Priority | Section | Item | What we're trying to fix | How we're fixing it | Effort | Risk / Win | Notes | Status | Date Fixed | Commit
1 | Q1-step1 | P0 | QUANT-1 Sunday follow-up | Re-derive Saturday's empirical analysis on n=384 750d backtest | Saturday's session changed live config based on agent-summarized stats. Agent's Fix 2 was actively wrong; Fix 3 had n=1 evidence in post-kill subset. Confirm Saturday's reads before any further changes. | Run inline Python script in SESSION_HANDOFF section 3 against cache/portfolio_backtest_750d_20260509_100501.json. Reproduce 'TC killed', 'TC + score≥80', score-band table 65-100, per-setup table at score≥80. | 5 min | Risk: none. Verify: TC killed PF 0.86, 80-85 band PF 1.72, VCP n=1. | Gate for everything below — do not proceed if numbers diverge. | OPEN
2 | Q1-step2 | P0 | QUANT-1 Sunday follow-up | Revert Fix 3 — VCP Breakout multiplier 1.2 → 0.0 | Saturday boosted VCP Breakout to 1.2× based on n=12 aggregate. Post-kill universe has only n=1 firing at score≥80, and it lost. | Edit config/config.json: setup_score_multiplier['VCP Breakout'] 1.2 → 0.0. Verify with git diff config/config.json. | 2 min | Risk: LOW. Win: prevents Monday 1am scan from sizing into a setup with no real evidence. | Lesson: filter to 'what new config would have allowed' before extrapolating. | OPEN
3 | Q1-step3 | P0 | QUANT-1 Sunday follow-up | Boost Near-VCP Breakout multiplier 0.7 → 1.0 | Post-kill universe at score≥80: Near-VCP Breakout n=50, PF 1.07 — workhorse currently demoted to 0.7×. | Edit config/config.json: setup_score_multiplier['Near-VCP Breakout'] 0.7 → 1.0. Verify next backtest. | 2 min | Risk: LOW-MEDIUM. Win: lets proven workhorse pull full weight. | PF 1.07 has wide CI 0.85-1.30 OOS. Verify with Q1-step4 250d backtest. | OPEN
4 | Q1-step4 | P0 | QUANT-1 Sunday follow-up | Run 250-day backtest to validate steps 2 + 3 | Need fast validation that config changes don't break things before committing 3 hours to full 750d. | python3 backtest.py --days 250 --hold 5 --min-score 65 --portfolio --equity 5000 --positions 4 --size-pct 0.25 > cache/logs/backtest_250d_quant1_$(date +%Y%m%d_%H%M%S).log 2>&1 & | ~12 min wall-clock | Risk: none (offline). Verify: PF ≥ 1.0 to proceed. | Output: cache/portfolio_backtest_250d_*.json. | OPEN
5 | Q1-step5 | P0 | QUANT-1 Sunday follow-up | Run 750-day backtest to confirm if 250d passes | Real evidence comes from full 750d window — same methodology that produced Saturday's headline n=384 result. | Same backtest command but --days 750. Run during Sunday daytime (3hr runtime). | ~3 hours | Risk: none. Verify: PF, WR, drawdown all directionally improved vs Saturday's PF 0.70. | Start by mid-morning Sunday so it finishes before Monday's 1am scan. | OPEN
6 | Q1-step6 | P0 | QUANT-1 Sunday follow-up | Consider buy_max_score: 90 in regime4_thresholds blocks | 90+ score band is anti-predictive: n=19, PF 0.32 in post-kill subset. | Add buy_max_score: 90 to each of 4 regime blocks under regime4_thresholds. Re-run final backtest. | 30 min + backtest | Risk: MEDIUM (small sample n=19). Win: removes -67% PF drag if real. | Skip if step 5 already shows PF healthy. | OPEN
7 | CLEAN-1 | P1 | Code Cleanup (DEFERRED) | backtest_v2.py — keep or delete? | 158-line file. docs/architecture.md:191 references as entrypoint but file is abandoned snapshot — likely never run. | ASK USER: 'Do you ever run backtest_v2.py?' If no → delete + update docs/architecture.md. | 10 min after answer | Win: -158 lines + clearer docs. | Phase 2 agent flagged but held back without user judgment. | OPEN
8 | CLEAN-3 | P1 | Code Cleanup (DEFERRED) | 8 standalone analysis scripts — ask user which still in use | Manual research scripts: audit_360.py (1320 lines!), analyze_backtest.py, analyze_signals.py, false_negatives.py, feature_importance.py, score_distribution_check.py, sensitivity.py, stop_width_sensitivity.py. | ASK USER per file: 'Do you ever run X?' For each 'no' → archive to _legacy/ or delete. ~3-5K lines win. | 30 min after answers | Win: ~3-5K lines if mostly stale. | audit_360.py is the biggest single file — start there. | OPEN
9 | OPS-1 | P1 | Operational Hygiene | Snapshot cleanup (scripts/cleanup_after_2026_05_16.sh) | Pre-Saturday session migration created intermediate snapshot files safe to remove after a week. | Run scripts/cleanup_after_2026_05_16.sh after 2026-05-16 cutoff. | 2 min | Win: cleaner repo. | Calendar reminder for 2026-05-16. | OPEN
10 | PERF-4 | P1 | Performance | Brotli compression (currently Gzip) | Server.py serves Gzip; Brotli typically reduces JSON/HTML transfer ~15% at similar CPU cost. | Add brotli middleware to FastAPI; negotiate via Accept-Encoding; verify Cloudflare passes encoding through. | 30 min | Win: -15% transfer size on data.json + tickers.json + HTML. | Verify Cloudflare tunnel doesn't strip br encoding. | OPEN
11 | PERF-5 | P1 | Performance | requestIdleCallback for _capScanAndDisableButtons | MutationObserver-based button disabler runs synchronously on init, blocking ~50ms. | Wrap call in requestIdleCallback(() => _capScanAndDisableButtons(), { timeout: 500 }). setTimeout fallback for Safari. | 15 min | Win: -50ms FCP. | Trivial fix; verify no race with first user interaction. | OPEN
12 | PERF-6 | P1 | Performance | Critical CSS extraction (775-line <style> → above-fold + lazy) | 775-line <style> in <head> blocks FCP; most rules govern below-fold content. | Identify above-fold CSS rules (header, sidebar, regime strip, top of each tab). Inline only those. Lazy-load rest via <link rel='stylesheet'> after init-end. | 1 hr | Win: -100ms FCP. |  | OPEN
13 | PERF-7 | P1 | Performance | Split data.json (5.3MB) into critical + deferred | Dashboard cold load now bound by 5.3MB data.json fetch + parse — bulk of remaining 644ms init-end. | Decompose data.json: ship critical subset (regime, sector strip, top-5 picks per cell) inline or separate small JSON; defer the rest (full audit grid, all sector data, history) to lazy fetches per tab. Update build_data.py + dashboard.html. | 4 hrs | Win: -300-800ms cold load (single largest remaining boot lever). | Biggest lever for next perf sprint. | OPEN
14 | QUANT-3 | P1 | Quant | Score-band filters per regime (e.g., min 70 in choppy) | Single buy_min_score per regime; needs band-specific filtering (e.g., choppy may benefit from 70-90 only). | Extend regime4_thresholds with optional score_band [lo, hi] per regime. Update decision_engine to honor band. Backtest each band per regime on 750d window. | 2-4 hrs | Sequence: AFTER Sunday QUANT-1 re-validation. |  | OPEN
15 | QUANT-4 | P1 | Quant | Walk-forward fold persistence (Supabase dual-write) | Walk-forward runs write to local cache only — hard to cross-compare or audit historical decisions. | Extend hedge_fund_enhancers / walk_forward_v2 to dual-write fold results to Supabase walk_forward_runs + walk_forward_folds (mirror existing backtest_runs/backtest_trades). | 1 hr | Win: cross-run analytics + audit trail. | Low priority — local cache works for now. | OPEN
16 | QUANT-5 | P1 | Quant | Mover predictor v3 — NLP earnings tone + options flow features | v1 had leakage. v2 fixed leakage but AUC stuck at 0.546 — pure technical features at entry don't predict mover success. | Build v3 with NEW feature classes (don't retrain): NLP earnings-call tone embeddings, options-flow IV skew + UOA put/call delta, catalyst-conditional models (subset by tag). A6 logger captures most inputs going forward. | days | Caveat: exploratory research, not config-tuning. | Don't retrain v1/v2 — both definitive AUC 0.546 negative. | OPEN
17 | QUANT-6 | P1 | Quant | Regime-conditional entries (rules vary per regime) | Same 5-pillar gates apply across all 4 regimes — real regimes have different optimal entry rules. | Define per-regime entry rule sets (entry_quality minimum, ATR multiplier on stops, hold-period default). Wire into analysis.py gate logic. Backtest per-regime to measure differential. | 4-6 hrs | Risk: MEDIUM (more knobs = more overfit risk). |  | OPEN
18 | MOD-2 | P1 | UI / Modularization | Pixel-diff regression baseline | After modularization, no automated visual-regression catch. | Playwright page.screenshot() snapshots per (tab × profile). Bake reference images into tests/snapshots/. CI fails on pixel-diff > 0.1%. | 2-3 hrs | Win: catches accidental layout regressions. |  | OPEN
19 | MOD-3 | P1 | UI / Modularization | Auth Playwright tests need SWING_USER / SWING_PASS env vars | 0[1-3]-*.spec.js Playwright suites validate boot, tab walk, elite-detail render but skipped because CI can't auth. | Add SWING_USER + SWING_PASS to local .env (already exists) and CI secret store. Update test runner to pull from env. Document in tests/README.md. | 5 min | Win: full auth-gated test coverage in CI. | Trivial. | OPEN
20 | CLEAN-4 | P2 | Code Cleanup (DEFERRED) | scripts/migrate_role_capabilities.py — cleanup after 2026-05-16 | One-shot CapStudio backfill. Already run. Tied to OPS-1 cleanup window. | Delete during OPS-1 cleanup pass after 2026-05-16. | 1 min | Win: -X lines. | Couples with OPS-1. | OPEN
21 | OPS-2 | P2 | Operational Hygiene | Uptime monitoring (launchd ping → dashboard) | Cloudflare healthcheck exists; no equivalent for FastAPI server itself or dashboard render. | launchd job pings http://localhost:7432/api/me every 5min (with auth). On 2 consecutive fails, Slack alert + log to data/uptime.jsonl. Status tile to dashboard system-status. | 1-2 hrs | Win: detect FastAPI hang independent of tunnel. |  | OPEN
22 | OPS-3 | P2 | Operational Hygiene | Admin endpoint for capability_registry edits | capability_registry.json hand-edited; risk of typo breaking RBAC; no audit trail. | PATCH /api/capability-registry/<entry_id> behind admin role. Validate against schema. Log to audit_log.jsonl. Optionally expose via settings_capstudio.html. | 2-3 hrs | Win: safer registry edits + audit trail. |  | OPEN
23 | OPS-4 | P2 | Operational Hygiene | CapStudio audit log UI | data/audit_log.jsonl captures PATCH /api/roles changes but no UI viewer. | Audit-log viewer in settings_capstudio.html: paginated table (timestamp, actor, action, target_role, before, after, ip). Filter by date / actor / role. | 2 hrs | Win: visibility into RBAC changes. |  | OPEN
24 | OPS-5 | P2 | Operational Hygiene | Backtest report manual 'regen' button | Hedge-fund backtest report regenerates only when new backtest finishes — must re-run full 3hr backtest for template changes. | Button in dashboard System Status tab triggers python3 hedge_fund_report.py --regen-only against latest cached backtest JSON. | 5 min | Win: fast iteration on report templates. | Trivial CLI wrapper. | OPEN
25 | MOD-1 | P2 | UI / Modularization | Scanner deep refactor | Scanner stays inline due to heavy let-bound state. Doesn't fit registry-driven module pattern cleanly. | Extract Scanner state into Zustand-style store (or simple module-scope object). Move render fn into infra/prototype/tabs/scanner/. Wire state via window event bus. | 1-2 hrs | Risk: low (works fine inline). Win: consistency. | Defer until next major refactor. | OPEN
26 | K6 | P0 | Architecture | Single canonical trade plan object — every tab reads from one source | Different dashboard tabs (Plan, Overview, Technicals, Models) computed their own derived values from raw signal data — drift risk, inconsistent UI numbers. | New canonical_trade_plan.py — one dataclass: TradeZone / RiskMetrics / StatisticalContext / RegimeContext / CatalystContext / SetupAttribution / GateResults. swing_trade.py attaches it per signal. Live Wilson-CI lookup from signal_log per setup×regime. Mechanism hypothesis per setup family. | shipped | Win: tabs converge on one truth; future tabs bind to dataclass fields. | 402 LOC. Future tabs MUST bind to canonical fields, not recompute. | DONE | 2026-05-09 | 2c9b9f339
27 | A6 | P0 | ML / Data Logging | Entry-time feature logger in swing_trade.py | ML mover-predictor v2 result (AUC 0.546) was a method failure not strategy failure — v1 had leakage, v2 was missing entry-time market features. Need to capture them going forward for catalyst-conditional ML. | Adds 30 entry-time fields to every signal_log entry, all prefixed `ef_`. Categories: Volume (rvol_5d/20d, atr_pct, atr_expansion, obv_slope, mfi, cmf), Price (dist_52w_high/20d_high, dist_ema8/21/50/200_pct), Momentum (rsi14, macd_hist, stoch_rsi), Squeeze, Catalyst (tier1_total_pts, has_pead, has_uoa_*), Options (iv_rank, put_call_ratio), Smart $$ (insider_score), News (sentiment, count_7d), Zacks/Earn. | shipped | Win: ~150-300 trades over 30 days → enough for catalyst-conditional ML retraining. | Pure additive — Wilson CI gates / hedge_fund_report / drift checker unaffected. | DONE | 2026-05-09 | 0574c60d4
28 | Q1-Fix1 | P0 | Quant / Config | Trend Continuation killed (Fix 1) | 750d backtest: Trend Continuation 264/384 trades (69%) at PF 0.65, Wilson LB 19.5% — single biggest portfolio drain. | config/config.json: setup_score_multiplier['Trend Continuation'] 0.7→0.0 + static_setup_kill_list dict entry (n=264, wr_lb=0.195, source=static). | shipped | Win: prevents biggest documented setup drag on Monday 1am scan. | Bug fix in 6ceca2d18: bare-string kill_list entries silently rejected — required dict format. | DONE | 2026-05-09 | fc76c9ec8 + 6ceca2d18
29 | Q1-Fix3 | P0 | Quant / Config | VCP Breakout multiplier 0.0 → 1.2 (Fix 3) — needs revert | Comment in config said VCP Breakout was 'removed from kill list' but value remained 0.0. Restored to 1.2 based on n=12 PF 1.79 aggregate. | config['setup_score_multiplier']['VCP Breakout']: 0.0 → 1.2. | shipped (revert candidate) | Risk: post-kill subset has only n=1 evidence — not real evidence. See Q1-step2. | REVERT CANDIDATE. Sunday plan step 2: revert to 0.0. | DONE | 2026-05-09 | fc76c9ec8
30 | K3 | P0 | Quant / Stop Engine | Stop must be at/below nearest fractal low | Calculated stops sometimes sit ABOVE the nearest Williams-fractal low — guaranteed easy stop-out target for market makers. | If stop > indicators['fractal_low'] (already computed in _williams_fractals at analysis.py:1089), widen DOWN to just below fractal low + 0.10×ATR buffer. Bounded: won't widen >20% from entry. | shipped | Win: single most important Vinod rule per coaching call. | Longs only. Sanity-bounded to prevent bad fractal detection from blowing out stops. | DONE | 2026-05-09 | 3d4eb71d7
31 | A2 | P0 | Strategy / Filter Layer | signal_filter.py — declarative whitelist gate | BUY decisions ran on raw 5-pillar score regardless of whether the (setup × regime × score_band × entry_quality) combo had backtest evidence behind it. | New signal_filter.py — demotes BUY→WATCH for non-whitelisted combos. _validations gate enforces n>=20 AND wr_lb>=0.40 per rule. Wired at decision_engine.py:626 after BUY threshold passes. 5/5 unit tests pass. | shipped | Win: prevents BUY in unproven combos. OFF by default until A5 attribution complete. | Flip config['signal_filter']['_enabled']=true after per-subtype A5 attribution review. | DONE | 2026-05-09 | 4129e5565
32 | A3 | P0 | Strategy / Filter Layer | Regime gate in compute_final_verdict | 750d evidence: strategy is bull-only. risk_off_trending and panic regimes returned negative expectancy. | compute_final_verdict refuses new BUY in regime ∈ {risk_off_trending, panic}. Returns verdict=WATCH with audit gate 'regime_gate' failed. Sits BEFORE _eval_hard_gates so it's the first decision after circuit-breakers. | shipped | Win: bull-only strategy, period. | Existing positions unaffected (exits run via separate paths). | DONE | 2026-05-09 | 1e40d30fc
33 | B1 | P1 | Backtest / Diagnosis | Diagnose --as-of-membership n_trades=0 bug | Walk-forward runs with --as-of-membership universe (~1000 tickers) returned n_trades=0 even though universe loader works correctly. | diagnose_as_of_membership.py — script captures findings. Root cause documented in SESSION_HANDOFF section 9. Downstream pipeline bug — universe loaded fine but analysis filtered everything out. | shipped (diagnosis); pending (fix) | Win: known root cause; fix will unblock historical backtesting at scale. | Fix deferred until standalone 750d backtest finishes. | DONE | 2026-05-09 | 9bc015562
34 | G3 | P1 | Infrastructure | signal_filter audit table + drift view | Need persistence + drift monitoring for signal_filter decisions before flipping it on. | migrations/003_signal_filter_audit.sql — signal_filter_decisions table + signal_filter_drift_30d view. Feeds A7 dashboard tile (future). | shipped | Win: audit + drift visibility before flipping signal_filter on. | A7 dashboard tile not yet built — registry has the data when needed. | DONE | 2026-05-09 | 4129e5565
35 | F11 | P1 | Infrastructure / Quality | Pre-commit hook for schema drift | Schema drift between JSON canonical files and Postgres columns silently fails dual-write to Supabase. Need CI-style enforcement. | First version: full-repo --strict check (commit 4129e5565). REFINED in 1e40d30fc: scoped to current commit — skips unless commit touches data/*.json OR migrations/ OR db.py; only blocks on NEW keys this commit adds. | shipped | Win: prevents NEW drift while not blocking on pre-existing technical debt. | 8 pre-existing JSON-only fields documented as tech debt. | DONE | 2026-05-09 | 1e40d30fc
36 | A5 | P1 | Quant / Forensics | Catalyst trade decomposition tool | Need to know WHICH catalyst sub-types drive performance (vs just the meta family). | decompose_catalyst_trades.py — outputs cache/catalyst_decomposition_*.html. Found pullback meta-pattern WR 53% / Wilson LB 44.6% / PF 1.83 (n=134) — at meta-family granularity. Per-subtype attribution still pending. | shipped (tool); pending (subtype attribution) | Win: forensic visibility into catalyst sub-performance. | A5-followup wired the meta-family Wilson rule into signal_filter (status DRAFT until subtype attribution). | DONE | 2026-05-09 | 1e40d30fc
37 | K1 | P1 | Quant / Stop Engine | Stop confluence with Fibonacci + EMA 50 | ATR-based stops were placed in isolation, ignoring proven structural levels (Fib retracements + EMA50). Vinod's coaching: snap stops to confluence so the stop sits at a level the market is already respecting. | compute_trade_plan in analysis.py:5223 — after ATR stop calculated, snap to highest-of-{Fib 0.382/0.5/0.618, EMA50} that's BELOW entry within 1.0% tolerance. Pulls stop UP to confluence (preserves R:R) when valid. Config: scoring.stop_confluence (enabled by default). | shipped | Win: stops at structural levels reduce noise stop-outs. | Longs only. Try/except wrapped — never fails trade_plan. | DONE | 2026-05-09 | 3d4eb71d7
38 | K2 | P1 | Quant / Stop Engine | VWAP/AVWAP below stop = risk_flag | When VWAP-20d or AVWAP-swing-low is below the stop, the trade is structurally weak (price already lost the volume-weighted reference). Vinod: this is a 'hard check.' | After plan finalized, append plan['risk_flags'] entry severity=high if VWAP-20d or AVWAP-swing-low < stop (longs). Soft-flag, does NOT block BUY (decision_engine surfaces). | shipped | Win: surfaces structurally weak trades without over-blocking. | Vinod said 'hard check' but blocking would over-fire — flag is right level. | DONE | 2026-05-09 | 3d4eb71d7
39 | K5 | P1 | Quant / Targets | Elliott Wave classification + Fib-extension targets | Default targets are ATR/resistance-based — under-target Wave-3 expansions. Vinod on HPE: 'Wave 3 Impulse, T1 50.37, T2 55.75' — Fib extensions of swing. | New classify_elliott_wave(df, lookback=90, fib_extensions=[1.272, 1.618]) heuristic Wave-3 detector. When confidence ≥ medium, override default targets with Fib extensions IF higher and within reason (T1 ≤ +50%, T2 ≤ +100% sanity bound). Exposes plan['elliott_wave'] for Models tab. | shipped | Win: more aspirational targets in confirmed impulse waves. | Wave 2 corrective + low-confidence Wave 3 informational only — don't override default targets. | DONE | 2026-05-09 | 302e9ea00
40 | J1 | P2 | Documentation | Update CLAUDE.md with new tools | New 2026-05-09 tools (canonical_trade_plan, signal_filter, apply_wf_proposals, morning_briefing, elite_research_note, hedge_fund_report, decompose_catalyst_trades, mover_predictor) not documented in CLAUDE.md path layout. | Added 8 file entries to Path Layout section. Annotations explain WHY each tool exists + key facts (e.g., mover_predictor AUC 0.546 — do not retrain). | shipped | Win: future Claude sessions discover new tools. |  | DONE | 2026-05-09 | 1e40d30fc
41 | J3 | P2 | Infrastructure | Git committer.email set globally | Commits attributed to phanirajgarimella@PhaniRajs-MacBook-Pro.local (hostname) instead of user's real email. | git config --global user.email phanirajgarimella@gmail.com. | shipped | Win: clean attribution in git log. |  | DONE | 2026-05-09 | 4129e5565
42 | CLEAN-2 | P2 | Code Cleanup (DEFERRED) | migrate_json_to_sqlite.py + migrate_sqlite_to_supabase.py | 231 + 440 = 671 lines of one-shot migration scripts already executed. | Keep until 2026-Q4 unless user explicitly says otherwise. Then delete + remove migration entrypoints from CLAUDE.md. | 5 min after answer | Win: -671 lines. | Standard data-migration retention practice. | DEFERRED
43 | MOB-1 | P2 | Mobile | Tablet portrait support (≥768px) | Desktop-first. Viewport meta added but no tablet layouts; sidebar overflows, tabs don't wrap. | @media (min-width: 768px) and (max-width: 1024px) breakpoint. Collapse sidebar to top nav, stack KPI tiles 2-up, ensure tabs scroll horizontally. | 4-6 hrs |  | Deferred — desktop is primary use case. | DEFERRED
44 | MOB-2 | P2 | Mobile | Phone support (≤480px) | No phone layout. Many UI elements unusable on phone. | Full mobile pass: hamburger nav, single-column stacking, ≥44px tap targets, swipe sub-tabs, condensed tables. | 8-12 hrs |  | Deferred indefinitely. | DEFERRED
45 | PERF-8-13 | P2 | Performance | Service worker, web worker, HTTP/2 push, skeleton screens, NDJSON streaming, SSR | Diminishing-returns optimizations after PERF-7 lands. | Each addresses a specific perceived-perf gap; defer until post-PERF-7 measurement identifies which one matters. | hours-days each | Win varies; defer until PERF-7 measured. | Don't pre-implement. | DEFERRED
46 | Q1-step7 | P0 | QUANT-1 Sunday follow-up | DO NOT add buy_max_score: 80 (the agent's Fix 2) | Capping at 80 would amputate the alpha zone (80-85 band, n=21, PF 1.72). | Explicit 'do not implement' guidance. Reject any agent suggestion to cap at 80. | n/a | n/a | Agents skim and miss post-filter subset analysis. | REJECTED

## Rollup
Status | P0 | P1 | P2 | Total
OPEN | 6 | 13 | 6 | 25
DONE | 7 | 7 | 2 | 16
DEFERRED | 0 | 0 | 4 | 4
REJECTED | 1 | 0 | 0 | 1
TOTAL | 14 | 20 | 12 | 46

## How to Update
Step | Command | What it does
1 | python3 scripts/update_open_items.py list | Show all items grouped by status
2 | python3 scripts/update_open_items.py list --open | Show only OPEN / IN_PROGRESS
3 | python3 scripts/update_open_items.py done <id> | Mark item DONE (auto-fills today's date + HEAD commit)
4 | python3 scripts/update_open_items.py done <id> --commit abc123 --date 2026-05-09 | Mark DONE with explicit commit/date
5 | python3 scripts/update_open_items.py status <id> IN_PROGRESS | Set arbitrary status (OPEN/IN_PROGRESS/DONE/DEFERRED/REJECTED)
6 | python3 scripts/update_open_items.py add NEW-ID P1 "Section" "Item title" "What" "How" | Add a new item to the registry
7 | python3 scripts/update_open_items.py xlsx | Regenerate this Excel from data/open_items.json
8 | edit data/open_items.json directly, then run xlsx | Free-form edits — works too