## Summary
SwingTrade Open Items — Summary
Category | Total | Done | Critical | High | Medium | Low | Open Effort (hrs)
A. Lock in working config | 7 | 0 | 1 | 3 | 2 | 1 | 18
B. Bugs | 4 | 1 | 1 | 0 | 2 | 0 | 6
C. Phase B (Supabase) | 8 | 3 | 0 | 1 | 4 | 0 | 14
D. Walk-forward | 4 | 3 | 1 | 0 | 0 | 0 | 6
E. Wilson CI / gates | 5 | 4 | 0 | 0 | 1 | 0 | 0
F. Reports + tooling | 11 | 10 | 0 | 0 | 0 | 1 | 0
G. Supabase migrations | 3 | 2 | 0 | 0 | 1 | 0 | 0
H. Strategy issues | 5 | 1 | 0 | 1 | 3 | 0 | 28
I. Operational | 4 | 1 | 1 | 1 | 0 | 1 | 0
J. Documentation | 3 | 0 | 0 | 0 | 2 | 1 | 0
K. Vinod feedback (HPE) | 11 | 0 | 1 | 7 | 1 | 2 | 21
TOTAL | 65 | 25 | 5 | 13 | 16 | 6 | 93
Critical Path (sequenced execution order)
# | ID | Item | Effort | Status
1 | K6 | Architectural fix: single canonical trade-plan output object — all tabs read from it | 1d | 🔴 critical
2 | K1 | Engine rule: Stop = Fibonacci + EMA 50 confluence (Rule P-new) | 3h | 🟠 high
3 | K2 | Engine rule: VWAP & AVWAP below stop loss = flag (Gate G1 sub-check) | 1h | 🟠 high
4 | K3 | Engine rule: stop placement at/below nearest fractal low (confirmed by Fib level) | 2h | 🟠 high
5 | K5 | Engine rule: EW classification + target derivation (Wave 3 Impulse → T1/T2 Fib extensions) | 4h | 🟠 high
6 | A1 | Promote A/B variant to production default (min_score=75, hold=7d) | 1h | 🔴 critical
7 | A2 | Build signal_filter.py with declarative whitelist gate | 2h | 🟠 high
8 | A3 | Regime gate in compute_final_verdict | 30m | 🟠 high
9 | K4 | Decide: add EMA 5 & EMA 13 to Technical pillar (5/13/21/50 vs current 8/21/50) | 1h decision + 2h impl | 🟡 medium
10 | A4 | Walk-forward validate the locked-in A/B config | 1h + 6h WF | 🟠 high
11 | A6 | Entry-time feature logger in swing_trade.py | 2h | 🟡 medium
12 | A5 | Catalyst-conditional analysis (per mover_predictor v2 conclusion) | 4h | 🟡 medium
13 | A7 | Drift dashboard tile in V2 dashboard | 2h | 🟢 low
Generated: 2026-05-09 22:31 · Source: generate_open_items_xlsx.py · 65 items

## All Items
ID | Category | Status | Priority | Item | Effort | Files Modified | Notes | Critical Path? | Owner | Blocks | Commit / Source
A1 | A. Lock in working config | 🔴 critical | 1 | Promote A/B variant to production default (min_score=75, hold=7d) | 1h | config/config.json | 60d backtest validates WR≥40%, PF≥1.4. A/B variant achieved PF 1.41 / +6.8% return. | Yes | me | A4
A2 | A. Lock in working config | 🟠 high | 2 | Build signal_filter.py with declarative whitelist gate | 2h | signal_filter.py (NEW), decision_engine.py:626 | Gates BUY→WATCH on (setup_type × regime × score_band × entry_quality). Whitelist seeded from current _validations. | Yes | me | A4
A3 | A. Lock in working config | 🟠 high | 2 | Regime gate in compute_final_verdict | 30m | decision_engine.py | Refuse BUY when regime is risk_off_trending or panic. Strategy is bull-only per 750d data. | Yes | me | A4
A4 | A. Lock in working config | 🟠 high | 2 | Walk-forward validate the locked-in A/B config | 1h + 6h WF | backtest/walk_forward_v2.py (run only) | Confirm test-fold PF ≥ 1.0 in ≥3 of 4 folds. Blocked by B1 fix. | Yes | me | A6, I3
A5 | A. Lock in working config | 🟡 medium | 3 | Catalyst-conditional analysis (per mover_predictor v2 conclusion) | 4h | decompose_catalyst_trades.py (NEW) | Subset 384-trade ledger to (earnings × insider × UOA × analyst-upgrade) buckets. Find WR > 60%. | Yes | me
A6 | A. Lock in working config | 🟡 medium | 3 | Entry-time feature logger in swing_trade.py | 2h | swing_trade.py | Log volume_surge, atr_expansion, breakout_clean, options_skew, catalyst_density per signal. Per d3e6127ff: ML failed because features weren't logged. | Yes | me
A7 | A. Lock in working config | 🟢 low | 4 | Drift dashboard tile in V2 dashboard | 2h | infra/prototype/tabs/status.js (or new sub-tab) | Surface output of LaunchAgents/com.swingtrade.driftalert.plist (cron exists, UI doesn't). | Yes | me
B1 | B. Bugs | 🔴 critical | 1 | --as-of-membership produces n_trades=0 in WF subprocesses | 2-4h | backtest.py (universe filter or analysis pipeline) | Universe lookup returns 1002 valid tickers but pipeline drops to 0 signals. Standalone repro: backtest.py --portfolio --days 250 --as-of-membership --min-score 60 --min-rs 60 | Yes | me | A4, D3
B2 | B. Bugs | 🟡 medium | 3 | Backtest enrich trade records with regime, entry_quality, sector | 1h verify + 1h add | backtest.py | Possibly already done by cb1f5a010 (backtest persistence) — verify before re-implementing. | No | me | A5
B3 | B. Bugs | ✅ done | 0 | WF subprocess timeout 3600s → 14400s | done | backtest/walk_forward_v2.py | Bumped to 4h to avoid premature kills under CPU contention. | No | me |  | 6222e4947
B4 | B. Bugs | 🟡 medium | 3 | Verify backtest persistence prevents silent overwrites | 30m | (verify only, no code change) | I observed cache/portfolio_backtest.json overwritten between reads. Confirm cb1f5a010 fixes this. | No | me
C1 | C. Phase B (Supabase) | ✅ done | 0 | state_layer.py shim built + 3 hot-path readers wired | done | state_layer.py, portfolio_tracker.py, signal_tracker.py, decision_engine.py |  | No | me |  | 310d91c34
C2 | C. Phase B (Supabase) | ✅ done | 0 | 2 more readers wired (swing_trade + build_data) | done | swing_trade.py:3376, infra/prototype/build_data.py |  | No | me |  | ec9bb006b
C3 | C. Phase B (Supabase) | ✅ done | 0 | 2 more readers in decision_engine | done | decision_engine.py |  | No | me |  | c55118c43
C4 | C. Phase B (Supabase) | 🟡 medium | 3 | Wire server.py alpaca-sync (read-modify-write) | 2h | server.py:802,824,860,866 | Complex pattern needs cache invalidation between reads + pt._save_state() for the write. | No | me
C5 | C. Phase B (Supabase) | 🟡 medium | 3 | Wire ~30 remaining cold-path readers | 4-6h | audit.py, audit_360.py, accuracy_framework.py, position_alerts.py, custom_tracker.py, etc. | Incremental low-value work. Defer until C4 + C6 done. | No | me | C6
C6 | C. Phase B (Supabase) | 🟠 high | 2 | Phase B.2 — flip SUPABASE_MODE=2 | 1h code + 1wk obs | .env | Run for 7 days. Monitor cache/state_layer_metrics.jsonl for fallback rate. Critical milestone toward cloud-canonical. | No | me | C5, C7
C7 | C. Phase B (Supabase) | 🟡 medium | 3 | Phase B.3 — stop JSON write, Supabase canonical | 2-3h | portfolio_tracker.py, signal_tracker.py, supabase_sync.py | Update state_backup.py to dump from Supabase nightly. | No | me | C8
C8 | C. Phase B (Supabase) | 🟡 medium | 3 | Phase B.4 — delete legacy JSON read paths | 2h | state_layer.py, migrate_sqlite_to_supabase.py | Convert migrate_sqlite_to_supabase.py → export_supabase_to_json.py (reverse direction for backup). | No | me
D1 | D. Walk-forward | ✅ done | 0 | tune_setup_multipliers + validate_multipliers_on_test + write_validations_from_folds | done | backtest/walk_forward_v2.py |  | No | me |  | 53ad7eb3d
D2 | D. Walk-forward | ✅ done | 0 | --config-override CLI on backtest.py | done | backtest.py |  | No | me |  | 53ad7eb3d
D3 | D. Walk-forward | 🔴 critical | 1 | Clean WF run end-to-end (blocked by B1) | 6h WF | backtest/walk_forward_v2.py (run only) | Last run died before fold 1 finished due to --as-of-membership bug. | No | me
D4 | D. Walk-forward | ✅ done | 0 | apply_wf_proposals.py exists | done | apply_wf_proposals.py | Ready when D3 produces output. | No | me |  | e5c7f0a14
E1 | E. Wilson CI / gates | ✅ done | 0 | Wilson CI gate on compute_setup_kill_list | done | decision_engine.py:240 |  | No | me |  | 3418ea745
E2 | E. Wilson CI / gates | ✅ done | 0 | static_setup_kill_list requires n≥10 + override flag | done | decision_engine.py |  | No | me |  | 3418ea745
E3 | E. Wilson CI / gates | ✅ done | 0 | setup_score_multiplier <1.0 reverts unless _validations declares n≥30 | done | analysis.py:8508 |  | No | me |  | 3418ea745
E4 | E. Wilson CI / gates | ✅ done | 0 | _validations populated for EMA21 (n=59) + 52wk (n=114) | done | config/config.json | Later expanded to all 6 setups by parallel session (d18cd5886). | No | me |  | 7d544c205
E5 | E. Wilson CI / gates | 🟡 medium | 3 | Wilson CI on setup_score_band_kills + _rejected_static audit visibility | 30m | decision_engine.py | Add LB check parallel to compute_setup_kill_list. | No | me
F1 | F. Reports + tooling | ✅ done | 0 | generate_session_report.py (8-section narrative) | done | generate_session_report.py |  | No | me |  | 079c2ac74
F2 | F. Reports + tooling | ✅ done | 0 | elite_research_note.py (institutional verdict) | done | elite_research_note.py |  | No | me |  | 3f56b6ce8
F3 | F. Reports + tooling | ✅ done | 0 | hedge_fund_report.py (12-section quant analytics) | done | hedge_fund_report.py | Auto-runs after every --portfolio backtest. | No | parallel |  | 4361c59a0
F4 | F. Reports + tooling | ✅ done | 0 | morning_briefing.py (priority-ordered action plan) | done | morning_briefing.py |  | No | me |  | e5c7f0a14
F5 | F. Reports + tooling | ✅ done | 0 | apply_wf_proposals.py (close the WF→config loop) | done | apply_wf_proposals.py |  | No | me |  | e5c7f0a14
F6 | F. Reports + tooling | ✅ done | 0 | check_schema_drift.py (JSON↔Postgres divergence) | done | check_schema_drift.py |  | No | me |  | 32c9e608f
F7 | F. Reports + tooling | ✅ done | 0 | mover_predictor v1 + v2 (definitive negative result) | done | mover_predictor.py, train_mover_predictor.py | AUC 0.546 — pure technical features at entry-time DO NOT predict mover success at 5d horizon. | No | parallel |  | 67b012ec2, d3e6127ff
F8 | F. Reports + tooling | ✅ done | 0 | hedge_fund_report train/test/holdout + k-fold + per-quarter | done | hedge_fund_report.py | Surfaced the PF 1.41 holdout finding — the pivotal insight. | No | parallel |  | 08c481198
F9 | F. Reports + tooling | ✅ done | 0 | Backtest persistence (parameterized snapshots) | done | backtest.py | Every --portfolio run writes both stable + parameterized snapshot. No more silent overwrites. | No | parallel |  | cb1f5a010
F10 | F. Reports + tooling | ✅ done | 0 | Daily drift alert cron | done | LaunchAgents/com.swingtrade.driftalert.plist | Runs model_drift_alert.py at 4:30pm PT. Slack alert when live WR diverges from backtest by >5pp. | No | parallel | A7 | d18cd5886
F11 | F. Reports + tooling | 🟢 low | 4 | Add check_schema_drift.py --strict to pre-commit hook | 30m | .git/hooks/pre-commit |  | No | me
G1 | G. Supabase migrations | ✅ done | 0 | 001_initial_schema.sql (17 tables) | done | migrations/001_initial_schema.sql |  | No | me |  | 079c2ac74
G2 | G. Supabase migrations | ✅ done | 0 | 002_backtest_runs.sql (3 tables) | done | migrations/002_backtest_runs.sql | backtest_runs, backtest_trades, walk_forward_folds. | No | me |  | 079c2ac74
G3 | G. Supabase migrations | 🟡 medium | 3 | 003_signal_filter_audit.sql (signal_filter_rejections table) | 30m | migrations/003_signal_filter_audit.sql (NEW) | Live audit trail for filter demotions. Goes with A2. | No | me | A2
H1 | H. Strategy issues | 🟠 high | 2 | Russell 1000 historical membership (Sharadar SF1) | $$ + 1d | data/membership/r1000_*.csv | Wikipedia doesn't have R1000 history. Sharadar SF1 ~$60/mo is the cleanest source. Cost-gated. | No | me
H2 | H. Strategy issues | ✅ done | 0 | Live-vs-backtest drift dashboard (cron exists) | done | model_drift_alert.py + LaunchAgents/com.swingtrade.driftalert.plist | Cron part done. UI surfacing is A7. | No | parallel |  | d18cd5886
H3 | H. Strategy issues | 🟡 medium | 3 | Phase 2 drawdown-aware sizing | 1d | portfolio_tracker.py, analysis.py | kelly_size.drawdown_mult is currently a no-op (multiplier=1.0). Wire equity history → sizing reduction during drawdown. | No | me
H4 | H. Strategy issues | 🟡 medium | 3 | Earnings ESP scanner (data already arrives, unused) | 4h | earnings_esp_scanner.py (NEW) | Per CLAUDE.md P0 priority. ESP data flows through but isn't acted on. | No | me
H5 | H. Strategy issues | 🟡 medium | 3 | Reconnect StockTwits / WSB / Congressional scrapers | 1d | data_fetcher.py | P0-3 partially shipped. Congressional Stock Watcher S3 endpoint dead. | No | me
I1 | I. Operational | ✅ done | 0 | Paper trading enabled (Day 9/60, started 2026-04-30) | done | data/paper_trading_start.json | Auto-disables 2026-06-29. | No | user
I2 | I. Operational | 🔴 critical | 1 | Decide before Day 60 (~2026-06-29): extend / live / shut down | decision | executor.py | Hard deadline. Strategy will auto-disable. | No | user
I3 | I. Operational | 🟠 high | 2 | After A1+A2+A4 ship, safe to consider live with validated A/B config | decision | executor.py --activate-live (NEW flag) | Gate: requires A1 (config promote), A2 (signal_filter), A4 (WF validation) all green. | No | user | I2
I4 | I. Operational | 🟢 low | 4 | Verify state_backup.py post-Mode-1 dual-write | 15m | state_backup.py |  | No | me
J1 | J. Documentation | 🟡 medium | 3 | Update CLAUDE.md with new tools | 30m | CLAUDE.md | signal_filter, mover_predictor, drift_alert, train/test/holdout, apply_wf_proposals, morning_briefing, check_schema_drift, OpenItems.xlsx. | No | me
J2 | J. Documentation | 🟢 low | 4 | docs/signal_filter_v1.md (whitelist source + retraining cadence) | 30m | docs/signal_filter_v1.md (NEW) | Goes with A2. | No | me | A2
J3 | J. Documentation | 🟡 medium | 3 | Set git committer.email globally | 5m | git config --global | Currently auto-derived as phanirajgarimella@PhaniRajs-MacBook-Pro.local — affects GitHub commit attribution. | No | me
K1 | K. Vinod feedback (HPE) | 🟠 high | 2 | Engine rule: Stop = Fibonacci + EMA 50 confluence (Rule P-new) | 3h | analysis.py (stop calc), config (gate G1) | Cat 1 — engine rule gap. Currently stop is engine-defined but confluence logic isn't specified. Becomes Gate G1 + scoring sub-rule. | Yes | me
K2 | K. Vinod feedback (HPE) | 🟠 high | 2 | Engine rule: VWAP & AVWAP below stop loss = flag (Gate G1 sub-check) | 1h | analysis.py (stop validation), decision_engine.py (gates) | Cat 1 — hard check. If VWAP < stop loss, stop placement is likely wrong. Add as entry validation rule. | Yes | me
K3 | K. Vinod feedback (HPE) | 🟠 high | 2 | Engine rule: stop placement at/below nearest fractal low (confirmed by Fib level) | 2h | analysis.py (stop calculation) | Cat 1 — missing from rulebook entirely. Stop should ALWAYS align with nearest fractal low. | Yes | me
K4 | K. Vinod feedback (HPE) | 🟡 medium | 3 | Decide: add EMA 5 & EMA 13 to Technical pillar (5/13/21/50 vs current 8/21/50) | 1h decision + 2h impl | analysis.py (technicals scoring), infra/prototype/tabs/technicals.js | Cat 1 — decide yes/no first, then implement. Changes Technical pillar scoring. Need to backtest before lock. | Yes | me
K5 | K. Vinod feedback (HPE) | 🟠 high | 2 | Engine rule: EW classification + target derivation (Wave 3 Impulse → T1/T2 Fib extensions) | 4h | analysis.py (EW model), infra/prototype/tabs/models.js | Cat 3 + EW gap. HPE example: Wave 3 Impulse, T1=$50.37, T2=$55.75 derived from Fib extensions of that wave. Wave 3 impulse = bullish. Fills one of the 7 design gaps. | Yes | me
K6 | K. Vinod feedback (HPE) | 🔴 critical | 1 | Architectural fix: single canonical trade-plan output object — all tabs read from it | 1d | decision_engine.py (compute_final_verdict), infra/prototype/* (all tab modules) | Cat 2 META-FIX — resolves K7+K8+K9. Engine outputs ONE canonical {entry_zone, stop, T1, T2, shares}. Every tab reads from that single output. No tab does independent calculation. Per the 2026-05-06 audit (7 independent decision engines) — that audit was supposed to fix this but didn't propagate to per-tab display. | Yes | me | K7, K8, K9
K7 | K. Vinod feedback (HPE) | 🟠 high | 2 | Output consistency: SMC trade plan must equal Overview tab's plan | (covered by K6) | infra/prototype/tabs/smc.js, plan.js | Cat 2 — single-source-of-truth problem. Auto-resolves when K6 ships. | Yes | me
K8 | K. Vinod feedback (HPE) | 🟠 high | 2 | Output consistency: Bear & Severe scenario cases must align with Plan/Thesis | (covered by K6) | infra/prototype/tabs/models.js (scenarios) | Cat 2 — scenario model outputs derived from same entry/stop/target as main plan. Auto-resolves with K6. | Yes | me
K9 | K. Vinod feedback (HPE) | 🟠 high | 2 | Output consistency: Thesis tab T1/T2 must match outlook numbers (no manual entry) | (covered by K6) | infra/prototype/tabs/plan.js, infra/prototype/tabs/overview.js | Cat 2 — same single-source fix. No tab should have its own independently calculated plan. | Yes | me
K10 | K. Vinod feedback (HPE) | 🟢 low | 4 | V2 backlog: mid-term fundamentals (4Q earnings + forward guidance + sector tailwind) | 1-2d (V2) | analysis.py (fund scoring), config (horizon profiles) | Cat 3 — product-scope decision. Means different score weights, macro inputs, exit rules per horizon. Current engine is implicitly swing (weeks-to-months). V2. | No | me
K11 | K. Vinod feedback (HPE) | 🟢 low | 4 | V2 backlog: long-term fundamentals (6Q + YoY comparison + forward guidance + sector tailwind) | 1-2d (V2) | analysis.py (fund scoring), config (horizon profiles) | Cat 3 — same V2 scope decision as K10. Long-term horizon variant. | No | me

## Critical Path
Critical Path — sequenced execution order
Step | ID | Item | Effort | Files | Verification | Blocks
1 | K6 | Architectural fix: single canonical trade-plan output object — all tabs read from it | 1d | decision_engine.py (compute_final_verdict), infra/prototype/* (all tab modules) | Open HPE elite-detail.html → Plan, Thesis, SMC, Models tabs all show identical entry/stop/T1/T2
2 | K1 | Engine rule: Stop = Fibonacci + EMA 50 confluence (Rule P-new) | 3h | analysis.py (stop calc), config (gate G1) | Stop value matches confluence of Fib retracement + EMA 50 within ±1%
3 | K2 | Engine rule: VWAP & AVWAP below stop loss = flag (Gate G1 sub-check) | 1h | analysis.py (stop validation), decision_engine.py (gates) | Test ticker with VWAP < stop → gate emits flag; pre-trade gate blocks BUY
4 | K3 | Engine rule: stop placement at/below nearest fractal low (confirmed by Fib level) | 2h | analysis.py (stop calculation) | Stop value ≤ nearest 5-bar fractal low for every BUY in next scan
5 | K5 | Engine rule: EW classification + target derivation (Wave 3 Impulse → T1/T2 Fib extensions) | 4h | analysis.py (EW model), infra/prototype/tabs/models.js | HPE Models tab shows Wave 3 Impulse with T1≈$50.37, T2≈$55.75 (Fib extensions)
6 | A1 | Promote A/B variant to production default (min_score=75, hold=7d) | 1h | config/config.json | 60d backtest WR≥40%, PF≥1.4 (matches A/B variant)
7 | A2 | Build signal_filter.py with declarative whitelist gate | 2h | signal_filter.py (NEW), decision_engine.py:626 | python3 swing_trade.py — flip _enabled and verify BUY count drops
8 | A3 | Regime gate in compute_final_verdict | 30m | decision_engine.py | Run scan during simulated risk_off regime — confirm zero BUYs
9 | K4 | Decide: add EMA 5 & EMA 13 to Technical pillar (5/13/21/50 vs current 8/21/50) | 1h decision + 2h impl | analysis.py (technicals scoring), infra/prototype/tabs/technicals.js | Backtest with new EMA stack improves Technical pillar correlation to PnL by ≥5%, then lock
10 | A4 | Walk-forward validate the locked-in A/B config | 1h + 6h WF | backtest/walk_forward_v2.py (run only) | ≥3 of 4 test folds show PF ≥ 1.0
11 | A6 | Entry-time feature logger in swing_trade.py | 2h | swing_trade.py | data/signal_log.json shows entry-time feature fields populated
12 | A5 | Catalyst-conditional analysis (per mover_predictor v2 conclusion) | 4h | decompose_catalyst_trades.py (NEW) | cache/catalyst_decomposition_*.html shows N catalyst-buckets with WR > 60%, n ≥ 20
13 | A7 | Drift dashboard tile in V2 dashboard | 2h | infra/prototype/tabs/status.js (or new sub-tab) | Drift status tile renders in V2 dashboard Status tab

## Done (audit trail)
Already shipped — audit trail
ID | Category | Item | Files | Commit | Notes
B3 | B. Bugs | WF subprocess timeout 3600s → 14400s | backtest/walk_forward_v2.py | 6222e4947 | Bumped to 4h to avoid premature kills under CPU contention.
C1 | C. Phase B (Supabase) | state_layer.py shim built + 3 hot-path readers wired | state_layer.py, portfolio_tracker.py, signal_tracker.py, decision_engine.py | 310d91c34
C2 | C. Phase B (Supabase) | 2 more readers wired (swing_trade + build_data) | swing_trade.py:3376, infra/prototype/build_data.py | ec9bb006b
C3 | C. Phase B (Supabase) | 2 more readers in decision_engine | decision_engine.py | c55118c43
D1 | D. Walk-forward | tune_setup_multipliers + validate_multipliers_on_test + write_validations_from_folds | backtest/walk_forward_v2.py | 53ad7eb3d
D2 | D. Walk-forward | --config-override CLI on backtest.py | backtest.py | 53ad7eb3d
D4 | D. Walk-forward | apply_wf_proposals.py exists | apply_wf_proposals.py | e5c7f0a14 | Ready when D3 produces output.
E1 | E. Wilson CI / gates | Wilson CI gate on compute_setup_kill_list | decision_engine.py:240 | 3418ea745
E2 | E. Wilson CI / gates | static_setup_kill_list requires n≥10 + override flag | decision_engine.py | 3418ea745
E3 | E. Wilson CI / gates | setup_score_multiplier <1.0 reverts unless _validations declares n≥30 | analysis.py:8508 | 3418ea745
E4 | E. Wilson CI / gates | _validations populated for EMA21 (n=59) + 52wk (n=114) | config/config.json | 7d544c205 | Later expanded to all 6 setups by parallel session (d18cd5886).
F1 | F. Reports + tooling | generate_session_report.py (8-section narrative) | generate_session_report.py | 079c2ac74
F2 | F. Reports + tooling | elite_research_note.py (institutional verdict) | elite_research_note.py | 3f56b6ce8
F3 | F. Reports + tooling | hedge_fund_report.py (12-section quant analytics) | hedge_fund_report.py | 4361c59a0 | Auto-runs after every --portfolio backtest.
F4 | F. Reports + tooling | morning_briefing.py (priority-ordered action plan) | morning_briefing.py | e5c7f0a14
F5 | F. Reports + tooling | apply_wf_proposals.py (close the WF→config loop) | apply_wf_proposals.py | e5c7f0a14
F6 | F. Reports + tooling | check_schema_drift.py (JSON↔Postgres divergence) | check_schema_drift.py | 32c9e608f
F7 | F. Reports + tooling | mover_predictor v1 + v2 (definitive negative result) | mover_predictor.py, train_mover_predictor.py | 67b012ec2, d3e6127ff | AUC 0.546 — pure technical features at entry-time DO NOT predict mover success at 5d horizon.
F8 | F. Reports + tooling | hedge_fund_report train/test/holdout + k-fold + per-quarter | hedge_fund_report.py | 08c481198 | Surfaced the PF 1.41 holdout finding — the pivotal insight.
F9 | F. Reports + tooling | Backtest persistence (parameterized snapshots) | backtest.py | cb1f5a010 | Every --portfolio run writes both stable + parameterized snapshot. No more silent overwrites.
F10 | F. Reports + tooling | Daily drift alert cron | LaunchAgents/com.swingtrade.driftalert.plist | d18cd5886 | Runs model_drift_alert.py at 4:30pm PT. Slack alert when live WR diverges from backtest by >5pp.
G1 | G. Supabase migrations | 001_initial_schema.sql (17 tables) | migrations/001_initial_schema.sql | 079c2ac74
G2 | G. Supabase migrations | 002_backtest_runs.sql (3 tables) | migrations/002_backtest_runs.sql | 079c2ac74 | backtest_runs, backtest_trades, walk_forward_folds.
H2 | H. Strategy issues | Live-vs-backtest drift dashboard (cron exists) | model_drift_alert.py + LaunchAgents/com.swingtrade.driftalert.plist | d18cd5886 | Cron part done. UI surfacing is A7.
I1 | I. Operational | Paper trading enabled (Day 9/60, started 2026-04-30) | data/paper_trading_start.json |  | Auto-disables 2026-06-29.